## WBS
Epic | Feature | User Story | Scoping | Version | M/D | Montant
Authentication & Core | Email Registration | As a user, I want to register with email and password so that I can create an account. | In Scope
Authentication & Core | Email Verification | As a user, I want to receive an email verification link so that I can activate my account. | In Scope
Authentication & Core | Register with Google account | As an end user, I want to sign up using my Google account so that I can create an account | In Scope |  |  | Added
Authentication & Core | Register with Apple account | As an end user, I want to sign up using my Apple account so that I can create an account | In Scope |  |  | Added
Authentication & Core | OAuth Login email address | As a user, I want to log in with email address so that I can access faster. | In Scope |  |  | Added
Authentication & Core | OAuth Login Google | As a user, I want to log in with Google so that I can access faster. | In Scope
Authentication & Core | OAuth Login Apple | As a user, I want to log in with Apple so that I can access faster. | In Scope
Authentication & Core | Log out | As an end user, I want to log out of my account so that I can securely end my session on the device. | In Scope |  |  | Added
Authentication & Core | Password Reset | As a user, I want to reset my password so that I can recover access. | In Scope
Authentication & Core | Role Selection | As a user, I want to choose my primary role so that I access relevant modules. | In Scope
Authentication & Core | Role Switching | As a user, I want to switch roles so that I can access additional features. | In Scope
Authentication & Core | Choose interested music genres | As a fan or instutition, I want to select my favorite genres so that I receive relevant content. | In Scope |  |  | Added
Authentication & Core | Choose my music genres | As a musician, I want to add music genres I play so that others know my style. | In Scope |  |  | Added
Authentication & Core | Choose interested city | As a fan, I want to choose my interested area so that I can discover music activities in locations I care about. | In Scope |  |  | Added
Authentication & Core | Choose activity city | As a musician or institution, I want to choose my activity area so that people can discover. | In Scope |  |  | Added
Authentication & Core | Session Management | As a platform, I want token-based authentication so that sessions are secure. | In Scope
Authentication & Core | Authorization / Permission | As a platform, I want to enforce role-based permissions | In Scope
Authentication & Core | Enforce Role-Based Access Control | As a platform, I want to restrict actions based on user permissions so that unauthorized actions are prevented. | In Scope
Authentication & Core | Restrict Unauthorized Actions | As a platform, I want to validate ownership of resources so that users can only modify their own content. | In Scope
Authentication & Core |  | As an admin, I want to assign or update user roles so that I can manage platform access levels. | In Scope
Authentication & Core | Data Export (GDPR) | As a user, I want to export my personal data so that GDPR is respected. | In Scope
Authentication & Core | KYC Upload ID | As a user, I want to upload ID documents so that I can be verified. | In Scope
Authentication & Core | Phone Verification | As a user, I want SMS verification so that my account is secured. | In Scope
Profile | Profile Creation | As a user, I want to add my basic information so that others understand who I am. | In Scope
Profile | Profile Completion / Validation | As a platform, I want to validate required profile fields so that profiles are meaningful. | In Scope
Profile | View Profile | As a user, I want to view my profile or other user's profiles so that I can see how the information appears. | In Scope |  |  | Added
Profile | Edit Profile | As a user, I want to edit my profile so that I can update information | In Scope
Profile | Profile Photo Upload | As a user, I want to upload a profile photo so that my account is personalized. | In Scope
Profile | Add Tags | As a user, I want to add tags so that I improve discoverability. | In Scope
Profile | Delete Account | As a user, I want to delete my account so that I control my data. | In Scope
Profile | Switch Account | As a user, I want to switch my account type in Settings (e.g., Professional, Teacher, Active musician, Composer, Amateur, Student, Fan, Institution) so that my profile reflects my current role on the platform. | In Scope |  |  | Added
Profile | Adaptive Profile Fields | As a platform, I want profile fields to adapt based on the user’s account status so that relevant information is collected and displayed. | In Scope |  |  | Added
Profile | Advertising Stories Subscription (Tier 1) | As a business, I want to subscribe to an Advertising Stories placement so that my brand is promoted to musicians and fans via story-format ads. | Out of Scope | A inclure V1 | 6.5 | 3334.5
Profile | Featured Placement in Specialized Tabs (Tier 2) | As a business, I want my profile featured in specialized tabs (e.g., Events, Marketplace, Training) so that I gain visibility among targeted users. | Out of Scope | A inclure V1 | 5 | 2565
Profile | News Feed Advertising (Tier 3) | As a business, I want to run ads in the main News Feed so that I can reach the broadest possible audience on the platform. | Out of Scope | A inclure V1 | 5 | 2565
Profile | Manage Ad Campaign | As a business, I want to create and manage my advertising campaigns so that I can control budget, duration, and targeting. | Out of Scope | A inclure V1 | 8 | 4104
Profile | View Ad Performance | As a business, I want to view impressions, clicks, and engagement metrics for my campaigns so that I can evaluate their effectiveness. | Out of Scope | A inclure V1 | 6.5 | 3334.5
Profile | Boost Artist Profile Visibility | As an artist, I want to pay to boost my profile visibility over a defined period so that I appear higher in search results and discovery feeds. | Out of Scope | A inclure V1 | 5 | 2565
Profile | Select Boost Duration | As a business, I want to choose the duration of my paid boost (e.g., 7, 14, or 30 days) so that I can control my advertising spend. | Out of Scope | A inclure V1 | 2 | 1026
Profile | View Boost Performance | As an artist, I want to see how many additional profile views and followers my boost generated so that I can assess the return on investment. | Out of Scope | A inclure V1 | 3 | 1539
Social Network | View Feed | As a user, I want to see a personalized feed so that I can discover content. | In Scope
Social Network | Infinite Scroll | As a user, I want infinite scrolling so that browsing is smooth. | In Scope
Social Network | Create Photo Post | As a user, I want to publish a photo post with a caption so that I can share content. | In Scope
Social Network | Create Video Post | As a user, I want to publish a video post with a caption so that I can share performances. | In Scope
Social Network | Add Tags to Post | As a user, I want to tag genres or instruments when creating a post so that my content is easier to discover. | In Scope |  |  | Added
Social Network | Edit Post | As a user, I want to edit my post so that I can update content. | In Scope
Social Network | View video posts | As a user, I want to view video posts so that I can watch and interact with video content | In Scope
Social Network | View post details | As a user, I want to open a post to view its full content and comments so that I can interact with it. | In Scope |  |  | Added
Social Network | Delete Post | As a user, I want to delete my post so that I control my content. | In Scope
Social Network | Like Post | As a user, I want to like posts so that I can show appreciation. | In Scope
Social Network | Comment Post | As a user, I want to comment so that I can interact. | In Scope
Social Network | Delete Comment | As a user, I want to delete my comment so that I control my content. | In Scope
Social Network | Create Story | As a user, I want to share a story so that I can post temporary updates. | In Scope |  |  | Added
Social Network | Highlight story | As a user, I want to highlight the story so that I can customize my stories | Out of Scope | A inclure V1 | 4 | 2052
Social Network | View Stories | As a user, I want to view stories from people I follow so that I can see quick updates. | In Scope |  |  | Added
Social Network | Follow User | As a user, I want to follow someone so that I see their posts. | In Scope
Social Network | Unfollow User | As a user, I want to unfollow someone so that I stop seeing content. | In Scope
Social Network | Media in Chat | As a user, I want to send images in chat so that I can share files. | In Scope
Social Network | Create Story | As a user, I want to publish a story so that I share temporary content. | In Scope
Social Network | Story Expiration | As a platform, I want stories to expire after 24h. | In Scope
Social Network | Report Post | As a user, I want to report inappropriate content. | In Scope
Social Network | Block User | As a user, I want to block someone so that they cannot contact me. | In Scope
Social Network | AI Moderation | As a platform, I want AI moderation so that content is filtered. | In Scope
Social Network | One-Time Donation | As a user, I want to donate to an artist. | In Scope
Social Network | Recurring Subscription | As a user, I want to subscribe monthly to an artist. | In Scope
Discovery & filters | View Explore Page (Home Feed) | As a user, I want to browse an explore page so that I can discover musicians, institutions, and content on the platform. | In Scope |  |  | Added
Discovery & filters | Search Users | As a user, I want to search for users so that I can find musicians, fans, or institutions. | In Scope |  |  | Added
Discovery & filters | Filter content | As a user, I want to filter search results by city, region, music genres or instrument so that I can discover specific content. | In Scope |  |  | Added
Community | View Group List | As a musician or fan, I want to browse a list of groups so that I can discover communities to join. | Out of Scope | Validé OOS | N/A | N/A
Community | View Group Details | As a user, I want to view a group’s details so that I can understand its members and purpose before joining. | Out of Scope | Validé OOS | N/A | N/A
Community | Create Group | As a musician or fan, I want to create a group so that I can gather people to play music together. | Out of Scope | Validé OOS | N/A | N/A
Community | Request to Join Group | As a musician or fan, I want to request to join group so that I can gather musicians to play music together. | Out of Scope | Validé OOS | N/A | N/A
Community | Cancel joinning request | As a musician or fan, I want to cancel my request to join group so that change my decision | Out of Scope | Validé OOS | N/A | N/A
Community | Track joinning request status | As a musician or fan, I want to see my request status so that I can track it | Out of Scope | Validé OOS | N/A | N/A
Community | Leave group | As a user, I want to leave a group so that I can exit the community. | Out of Scope | Validé OOS | N/A | N/A
Community | Approve or Reject Join Request | As a group owner, I want to approve or reject join requests so that I can control who joins the group. | Out of Scope | Validé OOS | N/A | N/A
Community | Delete group | As a group owner, I want to delete my group so that I can remove it when no longer needed. | Out of Scope | Validé OOS | N/A | N/A
Community | Create Bandmate Post | As a musician, I want to create a “looking for bandmates” post so that I can find people to play music with. | Out of Scope | Validé OOS | N/A | N/A
Community | View Bandmate Posts | As a musician, I want to browse “looking for bandmates” posts so that I can find opportunities to collaborate. | Out of Scope | Validé OOS | N/A | N/A
Monetization | View Donation Option | As a fan, I want to see a donation option on a musician’s profile so that I can support the artist financially. | In Scope |  |  | Added
Monetization | Select donation amount | As a fan, I want to enter or select a donation amount before making a payment so that I can decide how much to contribute. | In Scope
Monetization | Send Donation | As a fan, I want to donate to a musician so that I can support their work. | In Scope |  |  | Added
Monetization | Choose Donation Amount | As a fan, I want to select a donation amount so that I can decide how much I want to contribute. | In Scope |  |  | Added
Monetization | Receive Donations | As a musician, I want to receive donations from fans so that I can monetize my music and content. | In Scope |  |  | Added
Monetization | View Received Donations | As a musician, I want to view a simple history of donations I received so that I can track supporter contributions. | In Scope |  |  | Added
Monetization | Payment Processing | As a platform, I want to process donation payments securely via a payment provider so that transactions are reliable and safe. | In Scope |  |  | Added
Monetization | Security Messaging | As a user, I want to see security and payment information during the donation process so that I feel confident making a transaction. | In Scope |  |  | Added
Monetization | Subscribe to Musician | As a fan, I want to subscribe to a musician so that I can support them regularly. | In Scope |  |  | Added
Monetization | Manage Subscriptions | As a fan, I want to manage or cancel my subscriptions so that I can control recurring payments. | In Scope |  |  | Added
Monetization | View Subscribers | As a musician, I want to see my subscribers so that I understand my supporter base. | In Scope |  |  | Added
Safety / Trust | Report User | As a user, I want to report another user so that the platform can review inappropriate behavior. | In Scope |  |  | Added
Settings | Manage blocked User list | As a user, I want to manage block user list so that I can take any appropriate action | In Scope |  |  | Added
Settings | Unblock User | As a user, I want to unblock a user so that I can restore interaction if needed. | In Scope |  |  | Added
Settings | Review Reported Content | As a admin, I want to review reported content so that I can take appropriate action. | In Scope |  |  | Added
Settings | Take Moderation Action | As a admin, I want to remove content or restrict users who violate platform rules so that the community remains safe. | In Scope |  |  | Added
Settings | Enforce Music Content Policy | As a platform, I want to enforce music-related content guidelines so that the community stays focused on music. | In Scope |  |  | Added
Settings | Privacy Settings | As a user, I want to control which personal information is visible on my profile so that I can protect my privacy. | In Scope |  |  | Added
Messaging | Send Message | As a user, I want to send messages so that I can exchange information. | In Scope |  |  | Added
Messaging | Receive Message | As a user, I want to receive messages in real time so that I can respond quickly. | In Scope |  |  | Added
Messaging | View Conversation List | As a user, I want to see my conversations so that I can manage my chats. | In Scope |  |  | Added
Messaging | Read Receipt | As a user, I want to see if my message was read so that I know its status. | In Scope |  |  | Added
Notifications | Mark as Read | As a user, I want to mark notifications as read so that I can manage my inbox. | In Scope |  |  | Added
Notifications | Real-time Notification | As a user, I want to receive notifications in real time so that I don’t miss important events. | In Scope |  |  | Added
AI support | Ask Questions via AI Chat | As a user, I want to ask questions via AI chat so that I can get instant help when using the platform. | In Scope |  |  | Added
AI support | Receive AI Responses | As a user, I want to receive clear and helpful answers so that I can resolve my issues quickly. | In Scope |  |  | Added
Instrument Rental | Create Listing | As an owner, I want to create an instrument rental listing so that renters can find and book my instrument. | In Scope |  |  | Added
Instrument Rental | Add Photos | As an owner, I want to upload instrument photos. | In Scope |  |  | Added
Instrument Rental | Set Price | As an owner, I want to set rental price. | In Scope |  |  | This information will be included in Create listing, it should be treated as sub-task instead of a seprarated US
Instrument Rental | Set Availability | As an owner, I want to define availability dates. | In Scope |  |  | This information will be included in Create listing, it should be treated as sub-task instead of a seprarated US
Instrument Rental | Set Frequency | As an owner, I want to define rental duration options so renters know how long they can rent. | In Scope |  |  | This information will be included in Create listing, it should be treated as sub-task instead of a seprarated US
Instrument Rental | Add Instrument Details | As an owner, I want to provide instrument details so that renters understand the instrument condition. | In Scope |  |  | Added
Instrument Rental | Edit Instrument Details | As an owner, I want to edit instrument details so that I can update the instrument condition. | In Scope
Instrument Rental | Delete instrument | As an owner, I want to delete instrument so that the renter can not rent it | In Scope
Instrument Rental | Define Accommodation Availability | As an owner, I want to indicate whether accommodation or practice space is available with the instrument so that renters understand the rental conditions. | In Scope |  |  | Added
Instrument Rental | Provide Accommodation Details | As an owner, I want to describe the available accommodation or practice space so that renters know what facilities are provided. | In Scope |  |  | Added
Instrument Rental | Filter by Accommodation Availability | As a renter, I want to filter listings that include accommodation so that I can find instruments with a place to stay or practice. | In Scope |  |  | Added
Instrument Rental | View Accommodation Information | As a renter, I want to see accommodation details on the listing page so that I understand where the instrument can be used. | In Scope |  |  | Added
Instrument Rental | View Owner Profile | As a renter, I want to view the owner’s profile so that I can evaluate the instrument owner. | In Scope |  |  | Added
Instrument Rental | View Instrument Listing Details | As a user, I want to view detailed information about an instrument listing before sending a booking request. | In Scope |  |  | Added
Instrument Rental | Search Instruments | As a user, I want to search instruments so that I can find suitable listings. | In Scope |  |  | Added
Instrument Rental | Filter by Instrument Type | As a user, I want to filter instruments by type so that I can find the instrument I need. | In Scope |  |  | Added
Instrument Rental | Search by City | As a user, I want to filter by city. | In Scope |  |  | This information will be included in Search and Filter Instruments
Instrument Rental | Search by Price | As a user, I want to filter by price range. | In Scope |  |  | This information will be included in Search and Filter Instruments
Instrument Rental | Map View | As a user, I want a map view so that I see nearby instruments. | In Scope
Instrument Rental | Send Booking Request via Chat | As a renter, I want to request booking via chat | In Scope
Instrument Rental | Cancel booking request | As a renter, I want to cancel a request so that I can change my decision. | In Scope |  |  | Added
Instrument Rental | Track booking status | As a renter, I want to see the status of my requests so that I can track progress. | In Scope |  |  | Added
Instrument Rental | Accept Booking | As an owner, I want to accept booking. | In Scope
Instrument Rental | Reject Booking | As an owner, I want to reject booking. | In Scope
Instrument Rental | Booking Confirmation Email | As a renter, I want to receive a booking confirmation after the owner accepts my request. | In Scope |  |  | Update content
Instrument Rental | Pay Deposit | As a renter, I want to pay deposit (20–30%). | In Scope
Instrument Rental | Reminder Email | As a renter, I want payment reminder for balance. | In Scope
Instrument Rental | Complete full payment for rental | As a renter, I want to complete full payment so that I can confirm booking. | In Scope
Instrument Rental | View payment status | As a renter, I want to view my payment status so that I can track my payment progress | In Scope
Instrument Rental | Unlock Contact Details | As a renter, I want contact details unlocked after payment. | In Scope
Instrument Rental | Commission Calculation | As a platform, I want commission calculated automatically. | Out of Scope | A inclure V1 | 4 | 2052
Instrument Rental | Send Message to Owner | As a renter, I want to message the owner so that I can ask questions before booking. | In Scope |  |  | Added
Instrument Rental | Leave Review | As a renter, I want to leave review for renter after rental. | In Scope
Instrument Rental | Owner Review Visibility | As a renter, I want to see reviews from previous renters about the owner so that I can evaluate the reliability and quality of the instrument rental. | In Scope |  |  | Update content
Instrument Rental | Create Venue Rental Listing | As a venue owner, I want to list my venue where the instrument is available so that musicians can come and use the instrument | In Scope
Instrument Rental | Create Equipment Rental Listing | As an equipment owner, I want to list equipment available for rent so that musicians can find and book it. | In Scope
Instrument Rental | Book Venue or Equipment Rental | As a musician, I want to book a venue where the instrument is displayed so that I can reserve it for a specific date. | In Scope
Instrument Rental | Platform Commission on Rental | As a platform, I want to automatically collect a commission on each venue or equipment rental transaction so that revenue is generated. | Out of Scope | A inclure V1 | 4 | 2052
Instrument Sales | Create Sale Listing | As a seller, I want to create a sale listing with photos, description, and price so that buyers can view and purchase my instrument. | In Scope
Instrument Sales | Edit Sale Listing | As a seller, I want to edit my listing so that I can update information. | In Scope
Instrument Sales | Mark Listing as Sold | As a seller, I want to mark my listing as sold so that buyers know the instrument is no longer available. | In Scope |  |  | Added
Instrument Sales | Delete Sale Listing | As a seller, I want to delete my listing so that I can remove it from the marketplace. | In Scope
Instrument Sales | Browse Listings | As a buyer, I want to browse available listings so that I can find instruments. | In Scope
Instrument Sales | Filter instrument | As a buyer, I want to filter by instrument type or price so that I refine search. | In Scope
Instrument Sales | Search Listings | x | In Scope |  |  | Added
Instrument Sales | View seller listings | As a buyer, I want to view other listings from the same seller so that I can explore more instruments. | In Scope |  |  | Added
Instrument Sales | View Listing Details | As a buyer, I want to view listing details so that I evaluate the instrument. | In Scope
Instrument Sales | View seller profile | As a buyer, I want to view the seller's profile so that I can evaluate the seller before contacting them. | In Scope |  |  | Added
Instrument Sales | Message Seller | As a buyer, I want to contact the seller via private message so that I can negotiate. | In Scope
Instrument Sales | Receive Buyer Messages | As a seller, I want to receive messages from buyers so that I can respond to inquiries. | In Scope |  |  | Added
Instrument Sales | Report Listing | As a user, I want to report inappropriate listings so that the platform stays safe. | In Scope
Instrument Sales | Leave review | As a renter, I want to leave review for seller after buying | In Scope
Instrument Sales | Advanced Filters | As a buyer, I want advanced search filters (condition, brand, location). | In Scope
Instrument Sales | Commission on In-App Purchase | As a platform, I want to automatically collect a commission on each instrument or item purchase so that revenue is generated from marketplace transactions. | Out of Scope | A inclure V1 | 4 | 2052
Instrument Sales | Commission on In-App Sale | As a platform, I want to automatically collect a commission on each instrument or item sale so that revenue is generated from marketplace transactions. | Out of Scope | A inclure V1 | 3 | 1539
Music Partner Finder | Create Musician Profile | As a musician, I want to specify my level so that others know my experience. | In Scope |  |  | Change it to "Add Collaboration Info to Profile" feature
Music Partner Finder | Add Collaboration Info to Profile | As a musician, I want to specify my skill level and collaboration preferences so that others can evaluate compatibility. | In Scope
Music Partner Finder | Search by Instrument | As a musician, I want to filter by instrument so that I find relevant partners. | In Scope
Music Partner Finder | Search by Level | As a musician, I want to filter by skill level so that compatibility is ensured. | In Scope
Music Partner Finder | Search by Location | As a musician, I want to filter by city so that I find local partners. | In Scope
Music Partner Finder | Search Musicians for Collaboration | As a musician, I want to search for potential partners by keyword so that I can quickly find specific musicians. | In Scope |  |  | Added
Music Partner Finder | Filter Musicians for Collaboration | As a musician, I want to filter potential partners using available filters (location, instrument) and additional criteria (skill level, age, gender, availability) so that I can find compatible collaborators. | In Scope |  |  | Added
Music Partner Finder | Set Availability Date (profile-level) | As a musician, I want to set my availability date so that others know when I can collaborate. | In Scope |  |  | Added
Music Partner Finder | Map View | As a musician, I want a map view so that I see nearby profiles. | In Scope
Music Partner Finder | Send Collaboration Request via Chat | As a user, I want to send a collaboration request within a private conversation so that I can formally propose collaboration while chatting. | In Scope
Music Partner Finder | Cancel collaboration request | As a user, I want to cancel a request so that I can change my decision. | In Scope
Music Partner Finder | Track collaboration request status | As a user, I want to see the status of my requests so that I can track progress. | In Scope
Music Partner Finder | Accept Collaboration | As a user, I want to accept collaboration requests so that I confirm interest. | In Scope
Music Partner Finder | Reject Collaboration | As a user, I want to reject collaboration requests so that I decline politely. | In Scope
Music Partner Finder | Post-Meeting Review | As a user, I want to leave feedback after meeting so that others know my experience. | In Scope
Music Partner Finder | Auction Feature | As a platform, I want an auction feature for the instrument purchase | Out of Scope | Validé OOS | N/A | N/A
Music Partner Finder | Collaboration Confirmation Notification | As a user, I want an email confirmation when collaboration is accepted. | In Scope
Music Partner Finder | Post-Meeting Feedback Email | As a user, I want to receive a feedback request email after a collaboration so that I can leave a review. | In Scope |  |  | Added
Teaching | Create Teacher Profile | As a teacher, I want to create a teaching profile so that students can book lessons. | In Scope |  |  | Change it to "Add Teaching Information to Profile" feature
Teaching | Add Teaching Information to Profile | As a teacher, I want to add teaching details (instrument, experience, lesson format, pricing) so that students can book lessons. | In Scope |  |  | Added
Teaching | Add Experience | As a teacher, I want to add years of experience so that credibility is shown. | In Scope |  |  | Included in "Add Teaching Information to Profile" feature
Teaching | Set Lesson Format | As a musician, I want to define whether lessons are online or in-person so that students know how sessions are conducted. | In Scope |  |  | Added
Teaching | Set Availability | As a teacher, I want to set my available dates so that students know when I can teach. | In Scope |  |  | Added
Teaching | Upload Teaching Media | As a teacher, I want to upload photos and videos so that I can showcase my teaching style and attract students. | In Scope |  |  | Added
Teaching | Edit Teaching Information | As a teacher, I want to update my teaching information so that it remains accurate. | In Scope |  |  | Added
Teaching | Add Lesson Packages | As a teacher, I want to define lesson packages (1–20 sessions) so that students can choose suitable options. | In Scope
Teaching | Set Package Pricing | As a teacher, I want to set prices for each package so that students know the cost. | In Scope |  |  | Added
Teaching | Apply Package Discounts | As a teacher, I want to apply discounts for larger packages so that I can encourage bulk bookings. | In Scope |  |  | Added
Teaching | Edit Lesson Packages | As a teacher, I want to update or remove lesson packages so that I can manage my offerings. | In Scope |  |  | Added
Teaching | Search Teacher | As a student, I want to filter teachers by location, instrument, skill level, rating, availability, age, gender, and experience so that I can find suitable teachers. | In Scope
Teaching | Search by Reviews | As a student, I want to filter by ratings. | In Scope
Teaching | View Teacher Profile | As a student, I want to view a teacher’s profile so that I can evaluate their teaching service. | In Scope |  |  | Added
Teaching | View Teaching Content | As a student, I want to view teaching photos and videos so that I can assess teaching quality. | In Scope |  |  | Added
Teaching | View Map | As a student, I want to see teachers on a map so that I can find nearby instructors. | In Scope |  |  | Added
Teaching | Send Lession Request via Chat | As a student, I want to send a lesson request so that I can initiate booking. | In Scope
Teaching | Cancel lession request | As a student, I want to cancel a request so that I can change my decision. | In Scope
Teaching | Track lession request status | As a user, I want to see the status of my requests so that I can track progress. | In Scope
Teaching | Receive Lesson Requests | As a teacher, I want to receive lesson requests within a private conversation so that I can respond to students. | In Scope |  |  | Added
Teaching | Accept Lesson Request | As a teacher, I want to accept lesson requests within a private conversation | In Scope |  |  | Added
Teaching | Reject Lesson Request | As a teacher, I want to reject a request so that I can decline politely. | In Scope |  |  | Added
Teaching | Pay lesson deposit | As a student, I want to pay deposit so that booking is secured. | In Scope
Teaching | Complete full payment for lesson | As a student, I want to pay fully so that booking is completed. | In Scope
Teaching | Booking Confirmation Email | As a student, I want an email confirmation after booking. | In Scope
Teaching | Commission Calculation | As a platform, I want automatic commission calculation so that revenue is generated. | In Scope
Teaching | Post Lesson Review | As a student, I want to leave a review after lessons. | In Scope
Teaching | Pay Partial Amount | As a student, I want to pay partially so that booking is secured. | In Scope
Teaching | Pay Full Amount | As a student, I want to pay fully so that booking is completed. | In Scope
Teaching | Booking Confirmation Email | As a student, I want an email confirmation after booking. | In Scope
Teaching | Commission Calculation | As a platform, I want automatic commission calculation so that revenue is generated. | In Scope
Teaching | Post Lesson Review | As a student, I want to leave a review after lessons. | In Scope
Teaching | Service Client AI | As a user, I want AI assistance for booking issues. | In Scope
Teaching | Create Masterclass Listing | As an instructor, I want to create a paid masterclass with a description, date, and seat limit so that participants can discover and register. | In Scope
Teaching | Book a Masterclass Seat | As a student, I want to pay to reserve a seat in a masterclass so that my spot is confirmed. | In Scope
Teaching | Platform Commission on Masterclass Booking | As a platform, I want to automatically collect a commission on each paid masterclass seat booking so that revenue is generated. | In Scope
Teaching | Select Private Lesson Package | As a student, I want to choose a private lesson package (1, 5, 10, or 20 sessions) so that I can commit to a learning plan. | In Scope
Teaching | Pay for Private Lesson Package | As a student, I want to pay (credit cart or transfert) for my chosen lesson package so that sessions are confirmed and the teacher is notified. | In Scope
Teaching | Platform Commission on Private Lesson | As a platform, I want to automatically collect a commission on each private lesson package transaction so that revenue is generated. | In Scope
Concerts | Create Concert Page | As an organizer, I want to create a concert event with details (date, location, price, description) so that users can view and attend. | In Scope
Concerts | Add Concert Photos | As an organizer, I want to upload concert photos. | In Scope
Concerts | Edit Concert Event | As an organizer, I want to update concert details so that information remains accurate. | In Scope |  |  | Added
Concerts | Delete Concert Event | As an organizer, I want to remove my concert event so that it is no longer visible. | In Scope |  |  | Added
Concerts | Add Concert Details | As an organizer, I want to add date, location, price. | In Scope
Concerts | Search & Filter Concerts | As a user, I want to search and filter concerts by city, category, and music style so that I can find relevant events. | In Scope |  |  | Added
Concerts | Search by City | As a user, I want to search concerts by city. | In Scope
Concerts | Search by Style | As a user, I want to filter by music style. | In Scope
Concerts | Map View Concerts | As a user, I want map view for concerts. | In Scope
Concerts | View Concert Details | As a user, I want to view detailed concert info. | In Scope
Concerts | Add External Ticket Link | As an organizer, I want to add an external ticket purchase link so that users can buy tickets from a partner platform. | In Scope |  |  | Added
Concerts | Redirect to Ticket Platform | As a user, I want to be redirected to an external ticket site so that I can purchase tickets. | In Scope |  |  | Added
Concerts | Assign Concert Category | As an organizer, I want to categorize my concert so that users can discover it more easily. | In Scope |  |  | Added
Concerts | Manage Event Status | As an organizer, I want to update event status so that users know if it is upcoming or cancelled. | In Scope |  |  | Added
Concerts | Purchase Ticket In-App | As a user, I want to buy tickets directly within the app so that I can attend events without leaving the platform. | Out of Scope | A inclure V1 | 8 | 4104
Concerts | Platform Commission on Ticket Sale | As a platform, I want to automatically collect a commission percentage on each in-app ticket transaction so that revenue is generated from event sales. | Out of Scope | A inclure V1 | 4 | 2052
Concerts | Redirect to Third-Party Ticket Site | As a user, I want to be redirected to an external ticketing platform so that I can purchase tickets when in-app purchase is not available. | In scope | A inclure V1 | 1.5 | 769.5
Concerts | Track External Ticket Commission | As a platform, I want to track commission arrangements with third-party ticketing platforms so that affiliate revenue is recorded. | Out of Scope | Validé OOS | N/A | N/A
Concerts | Create Networking / Meetup Event | As a platform admin, I want to organize and publish networking or meetup events so that the community can connect in person. | Out of Scope | A inclure V1 | 4 | 2052
Concerts | Manage Speaker Compensation | As a platform admin, I want to select and record speaker compensation for meetup events so that speakers are paid and costs are tracked. | Out of Scope | Validé OOS | N/A | N/A
Concerts | Collect Meetup Event Revenue | As a platform, I want to collect ticket revenue from networking events after deducting speaker fees so that profit is generated from organized events. | Out of Scope | Validé OOS | N/A | N/A
Payment | Process Payment | As a platform, I want to process payments securely via a payment provider so that transactions are reliable and safe. | In Scope
Payment | Confirm Payment Transaction | As a user, I want to receive a confirmation after completing a payment so that I know the transaction was successful. | In Scope
Payment | Record Payment Transactions | As a platform, I want to record all successful payment transactions so that financial data remains accurate and traceable. | In Scope
Payment | View Transaction History | As a user, I want to view my transaction history so that I can track my completed payments across the platform. | In Scope
Institutions | Create Institution Profile | As an institution, I want to create a profile page. | In Scope |  |  | This uses "User Profile" module
Institutions | Upload Logo | As an institution, I want to upload a logo. | In Scope |  |  | This uses "User Profile" module
Institutions | Add Description | As an institution, I want to describe my organization. | In Scope |  |  | This uses "User Profile" module
Institutions | Browse Musicians | As an institution, I want to search musicians so that I can recruit talent. | In Scope |  |  | This uses "Discovery & filters" module
Institutions | Contact Musician | As an institution, I want to contact musicians directly. | In Scope |  |  | This uses "Message" module
Wallet | View Wallet Dashboard | As a user, I want to access a Wallet section in my settings so that I can see an overview of my income and expenses on the platform. | Out of Scope | A inclure V1 | 4 | 2052
Wallet | View Income Summary | As a user, I want to see a summary of all income received on the platform (donations, lesson fees, rental income, sales commissions) so that I can track my earnings. | Out of Scope | A inclure V1 | 3 | 1539
Wallet | View Expense Summary | As a user, I want to see a summary of all my expenses on the platform (bookings, subscriptions, ticket purchases, lesson packages) so that I can track my spending. | Out of Scope | A inclure V1 | 3 | 1539
Wallet | View Transaction History | As a user, I want to view a detailed chronological list of all my transactions (income and expenses) so that I can review individual entries. | Out of Scope | A inclure V1 | 2.5 | 1282.5
Wallet | Filter Transactions | As a user, I want to filter my transaction history by type (income/expense), category (rental, lesson, donation, subscription…), and date range so that I can find specific entries quickly. | Out of Scope | A inclure V2 | - | -
Wallet | View Financial Charts | As a user, I want to see graphs showing the evolution of my income and expenses over time so that I can analyse and compare profit versus 'loss' | Out of Scope | A inclure V2 | - | -
Wallet | View Balance | As a user, I want to see my current available balance on the platform so that I know how much I can spend or withdraw. | Out of Scope | A inclure V1 | 2 | 1026
Wallet | Receive Payout Notification | As a user, I want to receive a notification when income is credited to my wallet so that I stay informed of incoming payments. | Out of Scope | Validé OOS | N/A | N/A
Wallet | Top Up Wallet Balance | As a user, I want to add funds to my platform wallet using a payment method (card, bank transfer) so that I can spend within the app without re-entering payment details each time. | Out of Scope | A inclure V2 | - | -
Wallet | Pay with Wallet Balance | As a user, I want to pay for platform services (lessons, rentals, tickets, subscriptions) directly from my wallet balance so that checkout is faster. | Out of Scope | A inclure V2 | - | -
Wallet | Withdraw to Bank Account | As a user, I want to transfer my available wallet balance to my bank account so that I can access my earnings outside the platform. | Out of Scope | A inclure V2 | - | -
Wallet | Set Payout Method | As a user, I want to add and manage my bank account or payout method so that I can receive withdrawals from my wallet. | Out of Scope | A inclure V2 | - | -
Wallet | View Pending Payouts | As a user, I want to see the status of pending withdrawal requests so that I know when funds will arrive in my bank account. | Out of Scope | A inclure V2 | - | -
Wallet | Cryptocurrency Integration (Placeholder) | As a platform, I want to explore cryptocurrency top-up and spending capabilities so that users can transact using digital currencies in a future phase. | Out of Scope | A inclure V3 | - | -
Financial Rules & Config | Early Adopter Promotional Commission Rate | As a platform admin, I want to configure a reduced commission rate for early adopter users over a defined period so that we can attract our first users through preferential pricing. | Out of Scope |  | 2 | 1026
Financial Rules & Config | Apply Promotional Rate at Checkout | As a platform, I want to automatically apply the promotional commission rate when an eligible user completes a transaction so that the discount is seamless and transparent. | Out of Scope |  | 1.5 | 769.5
Financial Rules & Config | Display Promotional Rate to User | As a user, I want to see the promotional rate I am benefiting from during checkout so that I understand the discount I am receiving as an early adopter. | Out of Scope |  | 1 | 513
Financial Rules & Config | Rewards Program — Earn Points on Transactions | As a user, I want to earn reward points on every transaction I complete on the platform so that I am incentivised to continue using the platform's payment methods. | Out of Scope |  | 2 | 1026
Financial Rules & Config | Rewards Program — Unlock Preferential Commission Rate | As a user, I want to automatically unlock a lower commission rate once I reach a reward points threshold so that I clearly benefit from my loyalty to the platform. | Out of Scope |  | 2 | 1026
Financial Rules & Config | Rewards Program — View Points & Tier | As a user, I want to see my current reward points balance, my loyalty tier, and the benefits I have unlocked so that I understand my status and what I can earn next. | Out of Scope |  | 2 | 1026
Financial Rules & Config | Rewards Program — Admin Configure Tiers | As a platform admin, I want to configure loyalty tiers, point thresholds, and the associated commission discounts so that I can adapt the rewards program to business needs. | Out of Scope |  | 4 | 2052
Customer Service | AI Chatbot — Answer FAQ | As a user, I want to ask questions in the Feedback/Support section and receive instant answers from an AI assistant trained on the platform's knowledge base so that I get help without waiting for a human agent. | In scope
Customer Service | AI Chatbot — Escalate to Human Agent | As a user, I want to be automatically transferred to a human team member when the AI cannot answer my question so that I always receive a resolution. | Out of Scope | V2 | 2 | 1026
Customer Service | AI Chatbot — Learn from Human Answers | As a platform admin, I want new questions answered by human agents to be added to the AI knowledge base so that the AI continuously improves its ability to answer future questions automatically. | In scope
Customer Service | Submit Feedback / Support Request | As a user, I want to submit a support request or general feedback within the app so that I can report issues or share suggestions without leaving the platform. | Out of Scope | V3 | 1 | 513
Customer Service | Admin — View & Respond to Open Tickets | As a platform admin, I want to view all open support tickets escalated from the AI and respond directly to users so that no question goes unanswered. | In scope |  | 2 | 1026
Admin Dashboard | View Platform KPI Overview | As a platform admin, I want to see a dashboard with key performance indicators (total users, active users, transaction volume, generated revenue) so that I can monitor the health of the platform at a glance. | Out of Scope |  | 3 | 1539
Admin Dashboard | View User Growth Metrics | As a platform admin, I want to track user registration trends over time (daily, weekly, monthly) so that I can measure growth and the impact of acquisition campaigns. | Out of Scope |  | 2 | 1026
Admin Dashboard | View Transaction Volume | As a platform admin, I want to see total transaction volumes broken down by module (teaching, marketplace, events, rental) so that I understand which areas generate the most income. | Out of Scope |  | 2 | 1026
Admin Dashboard | View Revenue Breakdown | As a platform admin, I want to monitor revenue performance broken down by module (teaching, marketplace, events, rental) so that I can evaluate business results. | Out of Scope |  | 2 | 1026
User managment | View User list | As a platform admin, I want to view user list so that I can monitor platform adoption and engagement. | Out of Scope | V2 | 1 | 513
User managment | View User Details | As a platform admin, I want to view user profile details so that I can investigate account-related issues. | Out of Scope | V2 | 1 | 513
Transaction managment | View Transaction List | As a platform admin, I want to view a list of platform transactions so that I can monitor transaction activity and investigate issues. | Out of Scope | V2 | 1 | 513
Transaction managment | View Transaction details | As a platform admin, I want to view transaction details so that I can see the content of that | Out of Scope | V2 | 1 | 513
Commission management | Adjust Commission Rates | As a platform admin, I want to update commission rates per transaction type directly from the admin dashboard so that I can respond quickly to business needs without requiring a code deployment. | Out of Scope |  | 2 | 1026
Commission management | Commission Rate Change Audit Log | As a platform admin, I want every commission rate change to be logged with the admin's identity, previous value, new value, and timestamp so that changes are traceable and accountable. | Out of Scope |  | 1.5 | 769.5
Promotion managment | View Active Promotional Campaigns | As a platform admin, I want to view active promotional commission campaigns so that I can monitor current acquisition incentives. | Out of Scope |  | 1 | 513
Promotion managment | Create Promotional Campaign | As a platform admin, I want to create promotional commission campaigns so that I can attract new users and support marketing initiatives. | Out of Scope |  | 2 | 1026
Promotion managment | Edit Promotional Campaign | As a platform admin, I want to update promotional campaign settings so that I can adjust acquisition strategies based on business performance. | Out of Scope |  | 1 | 513
Promotion managment | Activate or Deactivate Promotional Campaign | As a platform admin, I want to activate or deactivate promotional campaigns so that I can control when promotional rates are applied. | Out of Scope |  | 0.5 | 256.5
Promotion managment | View Promotional Campaign Details | As a platform admin, I want to view detailed information about a promotional campaign so that I can understand its configuration and status. | Out of Scope |  | 0.5 | 256.5
Rewards Program management | View rewards program | As a platform admin, I want to view all rewards program tiers and benefits so that I can monitor the loyalty program configuration. | Out of Scope |  | 1 | 513
Rewards Program management | Create Rewards Tier | As a platform admin, I want to create rewards tiersso that I can incentivize users based on their activity. | Out of Scope |  | 2 | 1026
Rewards Program management | Configure Rewards Rules | As a platform admin, I want to define qualification rules for rewards tiers so that users can earn benefits based on platform usage. | Out of Scope |  | 3 | 1539
Rewards Program management | Configure Rewards Benefits | As a platform admin, I want to configure rewards benefits for each tier so that loyal users receive preferential commission rates or other incentives. | Out of Scope |  | 2 | 1026
Rewards Program management | Edit Rewards Program | As a platform admin, I want to update rewards program settings so that I can adapt loyalty strategies to business needs. | Out of Scope |  | 1 | 513
Rewards Program management | Activate or Deactivate Rewards Tiers | As a platform admin, I want to activate or deactivate rewards tiers so that I can control which loyalty programs are currently available. | Out of Scope |  | 0.5 | 256.5

## Project monitoring
Start date | Task | Owner | Status | Notes
| Define project overview |  | Completed
| 1st Kick-Off |  | Completed
| Design brief |  | Completed
| Wireframing |  | In progress
| WBS |  | In progress
| Create Acceptance Criteria based on WBS & Figma |  | Not started
| Review workflow with dev and QA team to make sure they all have information to develop and test |  | Not started
| Dev estimates WBS |  | Not started
| Check in/out scope |  | Not started
| Client negociation MVP, V2 |  | Not started
| Client validation wireframes |  | Not started
| Client validation for phase 2 |  | Not started
| Translate WBS to backlog |  | Not started
| Client pays for phase 2 |  | Not started
| Developpement done |  | Not started
| QA done |  | Not started
| Corrections added |  | Not started